## 2018
2020-2022 PHCA Improvement Budget Items
Improvement Item | Est. $ | Timing | 2013 | 2016 | 2020 | 2021 | 2022 | Comments
Permanent Pool Basketball Hoop | 2500 | Q1 | 1250 |  |  |  |  | Complete
Pool Deck resurfacing | 33000 | Q2 | 36733 |  |  |  |  | Complete
Pool Filter System repiping | 29950 | Q1 | 29950 |  |  |  |  | Complete
Clubhouse Sidewalk Path Lighting (poles) | 10000 | 2020 |  |  | 10000
Ping Pong Table replacement | 1000 | 2020 |  |  | 1000
Pool Deck replacement | 50000 | 2020 |  |  | 50000 |  |  | Based on condition and abilty to continue repairs
Parking lot repair/repainting | TBD | 2021 |  |  | n/a | TBD
Clubhouse interior painting | TBD | 2022 |  |  | n/a | n/a | TBD
Clubhouse furniture | TBD | 2022 |  |  | n/a | n/a | TBD
Unapproved Projects
Lighted Flagpole | 3500 | TBD | [5 empty] | Recommended by homeowner
Security Fencing & Access System | 40000 | TBD | [5 empty] | Security fencing & gate for lower parking lot, pool house access control, tennis court/tot lot access control
Security Camera Installation | 15000 | TBD | [5 empty] | Clubhouse, Pool, Parking & Tot Lots (if needed post fencing project)
Locking Backflow Preventer Enclosures | 750 | TBD | [5 empty] | May remove: theft has not been an issue
Tennis Court reservation system | TBD | TBD | [5 empty] | Justification of system still in debate; potential to utilize PHCA website
Updated message boards | TBD | TBD |  |  | 5 yrs
WiFi for Clubhouse and Pool | TBD | TBD
Adding lights to pool | TBD | TBD
Adding Pickle Ball lines to tennis courts | TBD | TBD | [5 empty] | Will include power washing courts
Adding lines to basketball goals | TBD | TBD
PHCA Planned Obsolence | Est. Cost | Life Expectancy |  |  | Years Remaining | Replacement Target
Clubhouse exterior painting | TBD | 8 years |  |  | 4 | 2024
Clubhouse interior painting | TBD | 8 years |  |  | 2 | 2022
Clubhouse furniture | TBD | 10 years |  |  | 2 | 2022
Clubhouse roof replacement | TBD | 20 years |  |  | 12 | 2032
Playground equipment replacement | TBD | 15 years |  |  | 8 | 2028
Parking lot repair/repainting | TBD | n/a |  |  | 1 | 2021
Clubhouse A/C Unit | 15000 | 15 years |  |  | 15 | 2034 |  | Replaced at end of 2019
Pool deck shade sail replacement | 5000 | 15 years |  |  | 14 | 2033 |  | Installed in 2019
Tennis courts lights | TBD | n/a |  |  | 5 | 2025
Parkling Lot lighting replacement | n/a | Ongoing |  |  | Ongoing | n/a |  | Ongoing maintenance
Split rail fence replacement | n/a | Ongoing |  |  | Ongoing | n/a |  | Ongoing maintenance